## Open Issues
No. | Issue Date | Issue Description | Classification | Consequence | Escalation | Owner | Support Personnel | Root Cause | Action Plan | Target Close Date | Next Follow-up Date
1 | 2021-10-28 | Front triangular rail A-surface end crushing/dent | Product Quality | Cosmetic Defect | 1 |  |  |  |  | 2022-03-15 | 2021-12-30
2 |  |  | Design Issues | Functional Failure | 2 |  |  |  |  | 2022-03-15 | 2022-01-30
3 |  |  | Schedule / Timeline | Durability Failure | 3 |  |  |  |  | 2021-11-30 | Close
4 |  |  | Commercial / Business | Dimensional Defect | 1 |  |  |  |  | 2021-11-30 | Close
5 |  |  | Communication | Cosmetic Defect | 2 |  |  |  |  | 2021-11-19 | Close
Status Key:
25% Issue Identified
50% Action Plan Proposed
75% Action Plan Implemented
100% Issue Resolved
Risk Level：
1 - manager Support
2 - work level Support
3 - Keep tracking