## sheet 1
Quality Open Issue List
Part No. | Issue Status | Cause Category |  |  |  |  | Issue Source | Severity | Responsible Department | Owner | D2-Description of Nonconformity | Occurrence Stage | Occurrence Date | Planned Closure Date | Actual Closure Date | D3-Containment | Break Point Date & Affected Lot | D4-Manufacturing Cause | D5-Manufacturing Countermeasure | Break Point Date | D4-Escape Cause | D5-Escape Countermeasure | Break Point Date | Issue Closure Criteria
|  | Process Control | Mould | Fixture | Gauge | Design | [17 empty] | D6-Countermeasure Progress / Effectiveness Verified | D7-FMEA Updated | D7-Control Plan Updated | D7-Work Instruction Updated | D8-Horizontal Deployment Completed | Additional Remarks
R300035366 | C | N | N | N | N | Y | AVES | C | Design | John | Surface scratches on cover plates ×5 | ET0 | 2022-07-20 | 2022-08-04 | 2022-08-04 | Conduct visual inspection to identify damaged armrest cover plates and arrange replacement. | 2022/7/20 LDP29H923PM001987 | Lack of rework work instructions; insufficient assessment of rework risks resulted in damage to the cover plate during rework of the armrest U-shaped bracket. | ① The U-shaped bracket has been corrected and no rework is required. ② Any subsequent rework activities must be carried out only after formal work instructions are issued. | 2022-07-21 | Due to unclear fixed-location identification in the GP12 inspection area, mixed parts occurred, resulting in reworked seats not being inspected in accordance with GP12 requirements. | Fixed-location layout and identification for the GP12 area have been completed. | 2023-08-04 | Y | Y | Y | Y | Y
B100099760 | C | N | N | N | Y | N | VQ | B | Process | John | Batch abnormal noise observed from the seat centre armrest when driving on Belgian road conditions at 10 km/h. | ET1 | 2022-12-15 | 2022-12-30 | 2022-12-30 | Screen components for abnormal noise by shaking. | 2022/12/15 LDP29H923PM002077 | System tolerance too tight: Sticking occurs at 0.05–0.1 mm, and abnormal noise occurs at ≥ 0.15 mm. The process window is too narrow and does not meet industrialisation requirements. | Design change: A 0.2 mm thick rib is added to the button base with a gradual increase in the Y-direction (inspection surface at 0 offset). | 2024-12-30 | Lack of a clear “no-rattle” acceptance criterion resulted in escape. | 100% measurement of fit/assembly clearance; specification: 0 to +0.05 mm. | 2024-12-30 | Y | Y | Y | Y | Y
E300030066 | Y | N | Y | Y | N | N | Testing | B | Process | John |  | PT1 | 2023-04-02 | 2023-04-17 | 2023-04-17
R500059866 | G | Y | N | N | N | N | Internal Control | A | Quality | John |  | SOP+1 | 2023-09-10 | 2023-09-25 | 2023-09-25
Severity Classification
Category A — Safety-related issues
Category B — Non-safety-related functional issues
Category C — Other issues
Issue Status
C — Closed
G — Pending Applicability
Y — In Progress
R — Delayed